## Action Tracker
Action ID | Description | TPR Area | Owner | Due Date | Status | Priority | Source | Created Date | Completed Date | Notes
ACT-001 | Complete security vulnerability remediation | Cyber Security | Jane Smith | 2026-06-15 | In Progress | Critical | Audit Finding | 2026-05-20 |  | Priority vulnerabilities identified in Q1 audit
ACT-002 | Submit AWS cost optimization proposal | AWS Cost Optimisation | Mike Johnson | 2026-06-10 | On Track | High | TPR Review | 2026-05-15 |  | Target 15% cost reduction
ACT-003 | Update architecture documentation | Architecture | John Doe | 2026-06-30 | Not Started | Medium | Tech Assurance | 2026-06-01 |  | Document cloud migration architecture decisions
ACT-004 | Renew Oracle license agreement | 3rd Party Contracts Management | Lisa Brown | 2026-07-01 | In Progress | Critical | Contract Expiry | 2026-05-01 |  | Contract expires July 31, negotiations underway
ACT-005 | Complete PI 2026.2 sprint planning | PI Delivery | Sarah Lee | 2026-05-31 | Completed | High | Agile Process | 2026-05-15 | 2026-05-30 | All teams completed sprint planning for Q3